## Sheet1
ITSC-3155 Software Engineering
Sprint Backlog
Story Tasks | Story Point | Assigned to | Estimated Effort | Day1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | Status | SPRINT REVIEW
User Story #1: Browse Menu | 8 |  | 18 | 7.5 | 4 | 8 | 1 | 1 | 0 | Done
Design DB schema for menu_items |  | Ramiro Alvarez-Cruz | 7 | 5 | 3 | 0 | 0 | 0 | 0 | Done | 0
Implement GET/api/menu_items |  | Ramiro Alvarez-Cruz | 8 | 1 | 1 | 5 | 0 | 1 | 0 | Done | 0
Implement GET/api/menu_items/{id} |  | Ramiro Alvarez-Cruz | 3 | 1 | 0 | 3 | 1 | 0 | 0 | Done | 0
User Story #2: Manage Menu Items | 13 |  | 11 | 14.5 | 6.5 | 1.5 | 2 | 1 | 0 | Done
POST /api/menu-items(create) |  | Ramiro Alvarex-Cruz | 3 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | Done | 2
PUT /api/menu-items/{id} |  | Ramiro Alvarex-Cruz | 3 | 5 | 1 | 0 | 1 | 1 | 0 | Done | 0
DELETE /api/menu-items/{id} |  | Ramiro Alvarex-Cruz | 5 | 9 | 5 | 1 | 1 | 0 | 0 | Done | 1
User Story #3: Register & Login | 5 |  | 17.5 | 4 | 0.5 | 3.5 | 4 | 1 | 0 | Done
Create customers table/model |  | Ramiro Alvarex-Cruz | 6 | 0 | 0 | 0 | 0 | 0 | 0 | Done | 0
POST /api/customers(register) |  | Ramiro Alvarex-Cruz | 8 | 3 | 0 | 3 | 3 | 0 | 0 | Done | 0
GET/PUT/DELETE /api/customers/{id} |  | Ramiro Alvarex-Cruz | 1.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 0 | Done | 0
pytest for registration |  | Ramiro Alvarex-Cruz | 2 | 0.5 | 0 | 0 | 0 | 0 | 0 | Done | 3
User Story #4: Place Orders | 8 |  | 25.5 | 8 | 13.5 | 13.5 | 5 | 2 | 0 | Done
Create orders & order_items tables |  | Ramiro Alvarex-Cruz | 9 | 4 | 2 | 2 | 1 | 1 | 0 | Done | 0
POST /api/orders |  | Ramiro Alvarex-Cruz | 6 | 3 | 3 | 3 | 3 | 1 | 0 | Done | 1
POST /api/orders/{id}/items |  | Ramiro Alvarex-Cruz | 6 | 0.5 | 8 | 8 | 1 | 0 | 0 | Done | 1
GET /api/orders/{id} |  | Ramiro Alvarex-Cruz | 4.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | Done | 0
User Story #5: Unit Test & Validation | 3 |  | 17 | 16.5 | 16.5 | 6.5 | 7 | 13 | 0 | Done
Pytest for menu & order flow |  | Samuel Glover | 2 | 1 | 1 | 1 | 0.5 | 1 | 0 | Done | 1
Validation & error handling |  | Ramiro Alvarex-Cruz | 6 | 6 | 6 | 0.5 | 3 | 9 | 0 | Done | 0
Documentation |  | Hector Villalpando | 7 | 9 | 9 | 4 | 3 | 3 | 0 | Done | 3
Integration check |  | Samuel Glover | 2 | 0.5 | 0.5 | 1 | 0.5 | 0 | 0 | Done | 1
TOTAL |  |  | 89 | 50.5 | 41 | 33 | 19 | 18 | 0 |  | 14