## Sheet1
ITSC-3155 Software Engineering
Sprint Backlog
Story Tasks | Story Point | Assigned to | Estimated Effort | Day1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | Status | SPRINT REVIEW
User Story #1: Guest Checkout | 8 |  | 18 | 7.5 | 4 | 8 | 1 | 1 | 0 | Done
Implement POST /api/orders/guest |  | Ramiro Alvarez-Cruz | 7 | 5 | 3 | 0 | 0 | 0 | 0 | Done | 0
Implement GET/api/orders/{order_id} |  | Ramiro Alvarez-Cruz | 8 | 1 | 1 | 5 | 0 | 1 | 0 | Done | 0
Unit test for making guest order |  | Ramiro Alvarez-Cruz | 3 | 1 | 0 | 3 | 1 | 0 | 0 | Done | 0
User Story #2: Menu Management | 13 |  | 11 | 14.5 | 6.5 | 1.5 | 2 | 1 | 0 | Done
Implement GET /api/menu-items |  | Ramiro Alvarex-Cruz | 3 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | Done | 2
Implement POST /api/menu-items |  | Ramiro Alvarex-Cruz | 3 | 5 | 1 | 0 | 1 | 1 | 0 | Done | 0
Implement DELETE /api/menu-items/{id} |  | Ramiro Alvarex-Cruz | 5 | 9 | 5 | 1 | 1 | 0 | 0 | Done | 1
User Story #3: Order Tracking | 5 |  | 17.5 | 4 | 0.5 | 3.5 | 4 | 1 | 0 | Done
Implement GET /api/orders/{order_id} |  | Ramiro Alvarex-Cruz | 6 | 0 | 0 | 0 | 0 | 0 | 0 | Done | 0
Ensure status changes are reflected correctly in tracking responses |  | Ramiro Alvarex-Cruz | 8 | 3 | 0 | 3 | 3 | 0 | 0 | Done | 0
Add unit test for tracking an order and seeing correct status |  | Ramiro Alvarex-Cruz | 1.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 0 | Done | 0
Implement GET /api/orders/track?code={tracking_code} |  | Ramiro Alvarex-Cruz | 2 | 0.5 | 0 | 0 | 0 | 0 | 0 | Done | 3
User Story #4: Payment Gateway | 8 |  | 25.5 | 8 | 13.5 | 13.5 | 5 | 2 | 0 | Done
Implement POST /api/payments |  | Ramiro Alvarex-Cruz | 9 | 4 | 2 | 2 | 1 | 1 | 0 | Done | 0
Implement GET /api/payments/{payment_id} |  | Ramiro Alvarex-Cruz | 6 | 3 | 3 | 3 | 3 | 1 | 0 | Done | 1
Prevent duplicate payment for the same order |  | Ramiro Alvarex-Cruz | 6 | 0.5 | 8 | 8 | 1 | 0 | 0 | Done | 1
Add unit test for successful payment |  | Ramiro Alvarex-Cruz | 4.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | Done | 0
User Story #5: Order Dashboard | 3 |  | 17 | 16.5 | 16.5 | 6.5 | 7 | 13 | 0 | Done
Implement GET /api/staff/orders |  | Samuel Glover | 2 | 1 | 1 | 1 | 0.5 | 1 | 0 | Done | 1
Implement PUT /api/staff/orders/{order_id}/status |  | Ramiro Alvarex-Cruz | 6 | 6 | 6 | 0.5 | 3 | 9 | 0 | Done | 0
Ensure orders are sorted |  | Hector Villalpando | 7 | 9 | 9 | 4 | 3 | 3 | 0 | Done | 3
Add unit test to verify status updates via staff endpoint |  | Samuel Glover | 2 | 0.5 | 0.5 | 1 | 0.5 | 0 | 0 | Done | 1
TOTAL |  |  | 89 | 50.5 | 41 | 33 | 19 | 18 | 0 |  | 14
User Story #6: Feedback System | 3 |  | 22 | 14 | 10 | 8 | 5 | 2 | 0 | Done
Implement POST /api/orders/{order_id}/feedback |  | Samuel Glover | 10 | 7 | 5 | 5 | 3 | 2 | 0 | Done | 1
Implement GET /api/orders/{order_id}/feedback |  | Ramiro Alvarex-Cruz | 4 | 5 | 3 | 2 | 0 | 0 | 0 | Done | 0
Implement GET /api/feedback |  | Hector Villalpando | 3 | 2 | 2 | 0 | 0 | 0 | 0 | Done | 3
Add unit test for creating and retrieving feedback |  | Samuel Glover | 5 | 0 | 0 | 1 | 2 | 0 | 0 | Done | 1
User Story #7: Promotion | 3 |  | 20 | 6 | 5 | 4 | 3 | 2 | 0 | Done
Implement POST /api/promotions |  | Samuel Glover | 8 | 3 | 3 | 2 | 0 | 2 | 0 | Done | 1
Implement GET /api/promotions |  | Ramiro Alvarex-Cruz | 5 | 1 | 2 | 1 | 1 | 0 | 0 | Done | 0
Implement DELETE /api/promotions/{id} |  | Hector Villalpando | 3 | 1 | 0 | 1 | 1 | 0 | 0 | Done | 3
Implement POST /api/orders/{order_id}/apply-promo |  | Samuel Glover | 4 | 1 | 0 | 0 | 1 | 0 | 0 | Done | 1
User Story #8: Data Analytics | 3 |  | 24 | 9 | 6 | 6 | 3 | 2 | 0 | Done
Implement GET /api/reports/sales/daily |  | Samuel Glover | 6 | 2 | 2 | 2 | 0 | 2 | 0 | Done | 1
Implement GET /api/reports/sales/top-items |  | Ramiro Alvarex-Cruz | 7 | 2 | 2 | 2 | 1 | 0 | 0 | Done | 0
Ensure date range filters work |  | Hector Villalpando | 4 | 1 | 1 | 1 | 1 | 0 | 0 | Done | 3
Add unit test for daily sales report endpoint |  | Samuel Glover | 7 | 4 | 1 | 1 | 1 | 0 | 0 | Done | 1
User Story #9: Documentation | 3 |  | 24 | 9 | 6 | 6 | 3 | 2 | 0 | Done
Create API overview documentation |  | Samuel Glover | 6 | 2 | 2 | 2 | 0 | 2 | 0 | Done | 1
Document all public endpoints |  | Ramiro Alvarex-Cruz | 7 | 2 | 2 | 2 | 1 | 0 | 0 | Done | 0
Create basic user/admin usage walkthrough |  | Hector Villalpando | 4 | 1 | 1 | 1 | 1 | 0 | 0 | Done | 3
Review and update documentation after final implementation changes |  | Samuel Glover | 7 | 4 | 1 | 1 | 1 | 0 | 0 | Done | 1